## Connector Tracker
Item # | Connector / App Name | Target System | Use Case Description | Requested By / Business Sponsor | Priority | Overall Status | Current Stage | Owning Team (API/Data Owner) | Team Contact | API Details Received? (Y/N) | Access/Permissions Requested Date | Access/Permissions Approved Date | API URI Intake Submitted Date | API URI Intake Approved Date | API URI Intake Ticket # | TDRC Submitted Date | TDRC Approved Date | TDRC Ticket # | Implementation Start Date | Implementation Complete Date | Testing / UAT Complete Date | Go-Live Date | SOAR Engineer Assigned | Blockers / Notes
1 | Example Connector A | Example Target System | Enrich alerts with reputation data | SOC Analytics Lead | High | In Progress | API URI Intake | Platform Engineering | Jane Doe | Y | 2026-06-01 | 2026-06-10 | 2026-06-12 |  | URI-1042 | [8 empty] | Waiting on intake board review
2 | Example Connector B | Example Target System 2 | Automate case creation from ticketing system | GSOC Manager | Medium | Not Started | Use Case Identification |  |  | N | [13 empty] | Need to confirm sponsor
3 | Example Connector C | Example Target System 3 | Pull threat intel indicators | Threat Intel Team | High | Completed | Go-Live | Threat Intel Eng | John Smith | Y | 2026-04-01 | 2026-04-08 | 2026-04-10 | 2026-04-20 | URI-0987 | 2026-04-22 | 2026-05-02 | TDRC-0456 | 2026-05-05 | 2026-05-20 | 2026-05-25 | 2026-05-27 | R. Singh

## Process Guide
SOAR Connector Onboarding — Process Guide
Step | Stage | Description | Tracker Column(s)
1 | Use Case Identification | Identify the business/security use case driving the need for a new connector. | D, E
2 | Team / API Contact | Identify the owning team for the target system and get API details from them. | I, J, K
3 | API Access & Permissions | Request API access with the right permissions/scopes from the owning team. | L, M
4 | API URI Intake | Submit to the API URI Intake governing body for formal approval of the endpoint/connection. | N, O, P
5 | TDRC Approval | Submit for Technical Design Review Committee (TDRC) approval once API URI Intake is approved. | Q, R, S
6 | Implementation | Engage engineering team to build/configure the SOAR connector. | T, X
7 | Testing / UAT | Validate connector functionality end-to-end before production use. | V
8 | Go-Live | Connector is live in production SOAR environment. | U, W
Note: Update 'Current Stage' and 'Overall Status' on the Connector Tracker tab as each connector moves through these steps.

## Dashboard
Connector Onboarding Dashboard
Status | Count
Not Started | 1
In Progress | 1
Blocked | 0
Completed | 1
On Hold | 0
Total Connectors Tracked | 3
By Stage
Stage | Count
Use Case Identification | 1
Team/API Contact | 0
API Access & Permissions | 0
API URI Intake | 1
TDRC Approval | 0
Implementation | 0
Testing | 0
Go-Live | 1